awesome — here’s a clean, phase-by-phase plan that treats backend + lessons as one parallel track, and does account for comms/review/debug. I also re-run the math assuming the backend dev joins content (2–3 h/day) once each phase’s backend is stable.

# Ground rules I used (so numbers make sense)

- People / hours

  - Backend dev: 2–3 h/day.

  - Two lesson devs: 3–4 h/day each.

  - After backend for a phase stabilizes, the backend dev joins content at 2–3 h/day.

- Lesson effort: ~12 h per finished lesson (includes QA/polish).

- Throughput (after 20–25% overhead for comms/review/debug)

  - While backend dev is busy → 2 lesson devs = ~3 lessons/week (avg)
(fast 4/wk · slow 2/wk).

  - After backend stabilizes → 3 lesson devs = ~4 lessons/week (avg)
(fast 5/wk · slow 3/wk).

- Stabilization buffer per phase (hotfixes, test rounds): 0.5–1.0 week (built in).

# Alpha Test (Current)

- We go rambo no backend yet, only test with people you really trust, finalize IOS as well

- I test 3 people, Chu tests 2 people

- Esimtate should be done next Friday (10/10/2025)

# FROM THEN:

## Phase 1 — Private Beta (target: 50–200 testers)

Frontend (app + lessons)

- Target: 20 total lessons (you have 5 → need +15).

- Ship: Chapter 1 (1–10) + a few from Chapter 2 (11–13) + your Qualitative Game.

- UX: lesson picker, onboarding, progress save/restore.

- Analytics: lesson_started, lesson_completed, time-on-task.

Backend (Cloud Functions + Firestore)

- Firestore Rules: deny client writes to /truth/**; allow write-only /intents/**.

- Functions (2–3): submitProgress, submitAnalytics, (optional) getMyProgress.

- Security: Auth + App Check enforced.

- Logs: structured (uid, lessonId, eventType, status).

Definition of done

- 20 lessons playable; all sensitive writes go via Functions; direct client → /truth/** blocked.

Time (weeks)

- FAST: ~3.9 wks

- AVERAGE: ~5.3 wks ← most realistic

- SLOW: ~7.3 wks

Why: backend needs ~2–4 weeks (by speed). During that, 2 devs produce lessons; after backend stabilizes, the backend dev adds ~1 lesson/week → raises velocity.

## Phase 2 — Public Beta (target: 200–1,000 testers)

Frontend

- Target: 40 total lessons (need +20).

- Ship: finish Chapter 2 (11–20) + most of Chapter 3 (21–27).

- UX: light streak/daily goal, checkpoints/quizzes, better navigation.

- Analytics: funnel (onboarding → first lesson → day-2 return).

Backend

- Validation + rate limiting (per UID/IP).

- Secrets → Secret Manager; third-party calls proxied by Functions.

- Monitoring: log-based alerts (errors, App Check failures, throttle hits).

Definition of done

- 40 lessons stable; limits/validation on hot endpoints; alerts live; secrets never in client.

Time (weeks)

- FAST: ~4.9 wks

- AVERAGE: ~6.5 wks ← most realistic

- SLOW: ~9.0 wks

## Phase 3 — Large-Scale Beta (target: 1,000–10,000 testers)

Frontend

- Target: 60 total lessons (need +20).

- Ship: finish Chapter 3 (21–30) + Chapter 4 (31–40) + start NN basics (41–45).

- UX: achievements, retention polish, perf trims (assets, lazy-load).

Backend

- Anomaly flags (impossible jumps), cooldowns.

- Cloud Tasks for retries / burst smoothing (analytics).

- Simple dashboards (Data Studio/Looker) over /truth/analytics.

Definition of done

- 60 lessons; anomalies auto-flagged; retries/queues solid; dashboards useful.

Time (weeks)

- FAST: ~4.9 wks

- AVERAGE: ~6.5 wks ← most realistic

- SLOW: ~9.0 wks

## Phase 4 — Launch (public stores; target: ~80 lessons)

Frontend

- Target: 80 total lessons (need +20).

- Ship: finish NN basics (41–50) + training (51–56); tee up “Season 2” as “coming next”.

- Polish: final UI pass, app-store assets, privacy/help pages.

- Retention hooks: weekly challenges, gentle win-backs (notifications/email).

Backend

- All 3rd-party APIs proxied (Stripe/OpenAI), receipts/entitlements server-side.

- Anti-fraud: IP/device correlation checks; stronger cooldowns.

- Ops: exports/backups, log retention, staged rollout plan.

Definition of done

- 80 lessons; monetization path safe; ops checklists ready; staged rollout.

Time (weeks)

- FAST: ~4.9 wks

- AVERAGE: ~6.5 wks ← most realistic

- SLOW: ~9.0 wks

# Roll-up (cumulative, from today; Alpha already done)

| Phase | Target lessons | FAST cum. | AVERAGE cum. | SLOW cum. |
| --- | --- | --- | --- | --- |
| Private Beta | 20 | 3.9 wks | 5.3 wks | 7.3 wks |
| Public Beta | 40 | 8.8 wks | 11.8–11.9 wks | 16.3 wks |
| Large-Scale Beta | 60 | 13.7 wks | 18.2–18.3 wks | 25.3 wks |
| Launch | 80 | 18.6 wks | 24.7–24.8 wks | 34.3 wks |

Most realistic (AVERAGE):

- Private Beta ≈ 5.3 weeks

- Public Beta ≈ 11.8–11.9 weeks (~3 months)

- Large-Scale Beta ≈ 18.2–18.3 weeks (~4.5 months)

- Launch (80 lessons) ≈ 24.7–24.8 weeks (~6.1–6.2 months)

Error bands:

- FAST ±15% · AVERAGE ±20% · SLOW ±30% (already reflected in bands via rates/buffers).

## Why this is tighter than earlier estimates

- Once backend stabilizes for a phase, that dev contributes ~1 lesson/week (2–3 h/day ≈ 12–15 h/week → ~1 lesson), lifting team velocity from ~3 → ~4 lessons/week (avg).

- Backend won’t be the bottleneck; content volume is.

## If you want to ship sooner

- Public Beta at 40 lessons around ~12 weeks (avg) is very doable.

- Market it as “Season 1: Intro to AI (40 lessons)” with new drops weekly to keep retention while you build to 80.

If you want, I’ll turn this into a one-page milestone checklist (who does what each week, exact backend endpoints/rules to add, and the lesson IDs to target) so you can track it without recalculating.